## Risks
Risk ID | Undesirable Event/Incident Scenario | Consequences | Severity/Impact | FoP/Probability | Rate | Risk | Decision/Actions
Executive Support
1 | Executives fail to support project Project objectives are not achieved because the project team lacks the authority. | T,D,I |  |  | 0 | Not rated
2 | Executives disengaged with project Project objectives are not achieved because stakeholders disregards project communications and meetings. | $,T,D,I |  |  | 0 | Not rated
3 | Conflict between executive stakeholders Project objectives are not achieved because members of executive management are combative to the project or there is a disagreement over project issues at the executive level. | T,D,I |  |  | 0 | Not rated
4 | Executive turnover Project objectives are not achieved because a key executive leaves the company/team. | T,D,I |  |  | 0 | Not rated
Stakeholders
5 | Stakeholders become disengaged Project objectives are not achieved because of stakeholders ignore project communications. | $,T,D,I |  |  | 0 | Not rated
6 | Project failure perception because of inaccurate expectations Stakeholders' inaccurate expectations may lead to the perception that the project has failed. (believe that the project will achieve something not in the requirements, plan, etc.). | I |  |  | 0 | Not rated
7 | Stakeholder turnover Project objectives are not achieved because of stakeholder turnover. | T,D |  |  | 0 | Not rated
8 | Stakeholders fail to support Project objectives are not achieved because of stakeholders have a negative attitude towards the project and wish to see it fail. | T,D |  |  | 0 | Not rated
9 | Stakeholder conflict Project objectives are not achieved because of disagreement between stakeholders over project issues. | T,D,I |  |  | 0 | Not rated
10 | Process inputs are low quality Project objectives are not achieved because inputs from stakeholders are low quality (e.g. business case, requirements, change requests). | T,D,I |  |  | 0 | Not rated
Project Scope
11 | Bad scope Project objectives are not achieved because the scope is not well defined. | $,T,D,I |  |  | 0 | Not rated
12 | Scope creep Project objectives are not achieved because of uncontrolled changes and continuous growth of scope. | $,T,D,I |  |  | 0 | Not rated
13 | Gold plating inflates scope Project objectives are not achieved because the project team add their own product features that aren't in requirements or change requests. | $,T,D,I |  |  | 0 | Not rated
14 | Estimates are inaccurate Project objectives are not achieved because of inaccurate estimates | $,T,D,I |  |  | 0 | Not rated
15 | Dependencies are inaccurate Project objectives are not achieved because dependencies dramatically impact the project schedule and costs. | $,T,D,I |  |  | 0 | Not rated
16 | Activities are missing Project objectives are not achieved because required activities are missing from scope definition | $,T,D,I |  |  | 0 | Not rated
Cost & Project Management
17 | Cost forecasts are inaccurate Project objectives are not achieved because of inaccurate cost estimates and forecasts. | $,F |  |  | 0 | Not rated
18 | Exchange rate variability Project objectives are not achieved because costs are incurred in foreign currencies exchange rates, which can have a dramatic impact. | $,F |  |  | 0 | Not rated
19 | Failure to follow methodology Project objectives are not achieved because of failure to follow methodology (i.e. scheduling, priorities). | $,T,D |  |  | 0 | Not rated
20 | Lack of management or control Project objectives are not achieved because lack of project management. | $,T,D |  |  | 0 | Not rated
Change Management (waterfall projects)
21 | Change management overload Project objectives are not achieved because of a large number of change requests. Which dramatically raises the complexity of the project and distracts key resources. | $,T,D,I |  |  | 0 | Not rated
22 | Stakeholder conflict over changes Project objectives are not achieved because of stakeholder conflict over proposed changes. | T,D,I |  |  | 0 | Not rated
23 | Project failure perception because of changes Large numbers of high priority change requests may lead to the perception that the project has failed. When the schedule and budget are continually extended — stakeholders may feel the project missed its original targets. | I |  |  | 0 | Not rated
24 | Lack of a change management system Project objectives are not achieved because of lack of tools to track and communicate changes. | $,T,D |  |  | 0 | Not rated
25 | Lack of a change management process Project objectives are not achieved because of limited visibility into changes that impact the project. | $,T,D |  |  | 0 | Not rated
26 | Lack of a change control board Objectives of a large project are not achieved because of lack of a change control board to manage changes | $,T,D |  |  | 0 | Not rated
27 | Inaccurate change priorities Project objectives are not achieved because of inaccurate change priorities. When non-essential changes are prioritized impacting critical schedules. | T,D |  |  | 0 | Not rated
28 | Ambiguous change requests Project objectives are not achieved because of low quality of change requests. | $,T,D |  |  | 0 | Not rated
29 | Confliction change requests Project objectives are not achieved because of change requests that make no sense in the context of the requirements. | D,I |  |  | 0 | Not rated
Communication
30 | Project team misunderstand requirements Project objectives are not achieved because the project team misunderstand requirements | $,T,D,I |  |  | 0 | Not rated
31 | Communication overhead Project objectives are not achieved because key project resources spend a high percentage of their time engaging stakeholders on project issues and change requests. | T |  |  | 0 | Not rated
32 | Under communication Project objectives are not achieved because of inappropriate communication between team, stakeholders and users. | D,I |  |  | 0 | Not rated
33 | Users have inaccurate expectations Users' inaccurate expectations may lead to the perception that the project has failed (i.e. users don't understand the product that's coming their way). | U |  |  | 0 | Not rated
Team
34 | Resource shortfalls Project objectives are not achieved because of inability to secure sufficient resources for the project. | $,T,D |  |  | 0 | Not rated
35 | Insufficient knowledge/skills Project objectives are not achieved because of learning curves lead to delays and cost overrun. | $,T |  |  | 0 | Not rated
36 | Training isn't available Project objectives are not achieved because lack of appropriate training for missing skills. | T,D |  |  | 0 | Not rated
37 | Training is inadequate Project objectives are not achieved because team members are not fully productive in a new skill. | T,D |  |  | 0 | Not rated
38 | Team members are inexperienced Project objectives are not achieved because team members are not fully productive due to lack of experience. | T |  |  | 0 | Not rated
39 | Performance issues Project objectives are not achieved because team members perform below expectations. | $,T,D,I |  |  | 0 | Not rated
40 | Negative attitude Project objectives are not achieved because team members have negative attitudes towards the project and may actively or passively sabotage project efforts. | T,D |  |  | 0 | Not rated
41 | Resource turnover Resource turnover leads to delays and cost overrun. | $,T,D,I |  |  | 0 | Not rated
42 | Low team motivation Project objectives are not achieved because team members lack motivation. This is a particularly common risk for long running projects. | D |  |  | 0 | Not rated
43 | Lack of commitment from functional managers Project objectives are not achieved because lack of commitment from functional managers. In a matrix organization your team may report to functional managers. These functional managers are important stakeholders whose support is critical. | T,D |  |  | 0 | Not rated
Architecture
44 | Architecture is infeasible Project objectives are not achieved because the selected architecture is impossible to implement, excessively costly or doesn't support the requirements. | $,T,D |  |  | 0 | Not rated
45 | Architecture is not fit Project objectives are not achieved because the selected architecture is low quality and not fit for purpose. | $,T,D |  |  | 0 | Not rated
46 | Architecture fails to pass governance processes Project objectives are not achieved because the selected architecture fails to pass technology governance processes (i.e. PCI DSS compliance). | $,D |  |  | 0 | Not rated
47 | Architecture lacks flexibility Project objectives are not achieved because the selected architecture is incapable of supporting change requests and needs to be reworked. | $,T,D |  |  | 0 | Not rated
Design
48 | Design is infeasible Project objectives are not achieved because the selected design is impossible to implement, excessively costly or doesn't support the requirements. | $,T,D |  |  | 0 | Not rated
49 | Design is not fit Project objectives are not achieved because the selected design is low quality and not fit for purpose. | $,T,D |  |  | 0 | Not rated
50 | Design lacks flexibility Project objectives are not achieved because the selected design makes change requests difficult and costly. | $,T,D |  |  | 0 | Not rated
51 | Design uncomfortable for users Project objectives are not achieved because the selected design has high level of user complains (i.e. low quality from user point of view). | D,U |  |  | 0 | Not rated
Technical
52 | Technology components aren't fit for purpose Project objectives are not achieved because technology components are low quality. | $,D |  |  | 0 | Not rated
53 | Technology components aren't scalable Project objectives are not achieved because technology components can't be scaled to meet performance demands. | $,D,S |  |  | 0 | Not rated
54 | Technology components aren't extensible Project objectives are not achieved because technology components are difficult to extend with new capabilities. | $,D,S |  |  | 0 | Not rated
55 | Technology components aren't interoperable Project objectives are not achieved because technology components lack standard interfaces and/or integration. | $,D,S |  |  | 0 | Not rated
56 | Technology components violate best practices Project objectives are not achieved because technology components aren't compliant with standards and best practices. | $,D,L |  |  | 0 | Not rated
57 | Technology components have security vulnerabilities Project objectives are not achieved because technology components have known unfixable security vulnerabilities. | D,S |  |  | 0 | Not rated
58 | Technology components are over-engineered Project objectives are not achieved because technology components are bloated with unneeded functionality and design features. | $,D |  |  | 0 | Not rated
59 | Technology components lack stability Project objectives are not achieved because technology components lack stability (i.e. crash). | D,S |  |  | 0 | Not rated
60 | Technology components aren't reliable Project objectives are not achieved because technology components fail after a short time. | D,S |  |  | 0 | Not rated
52 | Date leakage Project objectives are not achieved because of security incidents during the project (e.g. information or test data are leaked). | D,R,U |  |  | 0 | Not rated
53 | System outages Project objectives are not achieved because critical systems go down (i.e. code repository, test environments, shared file or DB server) | T,D |  |  | 0 | Not rated
54 | Legacy components lack documentation Project objectives are not achieved because of integration with undocumented legacy components. | T,D |  |  | 0 | Not rated
55 | Legacy components are out of support Project objectives are not achieved because of integration with legacy components that are no longer in support. | T,D,S |  |  | 0 | Not rated
56 | Components or products aren't maintainable Project objectives are not achieved because of integration with technology components, tools or platforms that are difficult to maintain (e.g. lacking documentation, rare skills, complex or experimental). | D,S |  |  | 0 | Not rated
57 | Components or products can't be operationalized Project objectives are not achieved because of criteria for operationalization of new systems aren't met. | D,S |  |  | 0 | Not rated
58 | Project management tool problems & issues Project objectives are not achieved because project management tools have technical problems. | T,D |  |  | 0 | Not rated
Integration
59 | Delays to required infrastructure Project objectives are not achieved because delays to infrastructure such as hardware or software. | $,T |  |  | 0 | Not rated
60 | Failure to integrate with business processes Project objectives are not achieved because the product fails to fit into the existing business processes. | F,D |  |  | 0 | Not rated
61 | Failure to integrate with systems Project objectives are not achieved because the product fails to integrate with existing systems. | F,D |  |  | 0 | Not rated
62 | Integration testing environments aren't available Project objectives are not achieved because environments to test integration aren't available. | D |  |  | 0 | Not rated
63 | Failure to integration with the organization Project objectives are not achieved because the project fails to integrate with the organization. This happens when the project is focused on delivering something specific and fails to look at the organization as a whole. | F,D,I,R |  |  | 0 | Not rated
64 | Failure to integrate components Project objectives are not achieved because product components fail to integrate with each other. This can represent a significant risk when you've outsourced work to a large number of vendors. | $,D |  |  | 0 | Not rated
65 | Project disrupts operations Project objectives are not achieved because the project disrupts business operations and damage the organization's financial results. | F,R,U,I | 4-Major |  | 0 | Not rated
66 | Project disrupts sales Project objectives are not achieved because the project disrupts sales effectiveness. | U,I | 3-Moderate |  | 0 | Not rated
67 | Project disrupts compliance Project objectives are not achieved because the project disrupts compliance processes such as audits and reporting. | L,R,I | 3-Moderate |  | 0 | Not rated
Requirements
68 | Requirements not align with strategy Project objectives are not achieved because requirements conflict with the organization's strategy. | D,I |  |  | 0 | Not rated
69 | Requirements not align with business processes Project objectives are not achieved because requirements fail to align with business processes. | D |  |  | 0 | Not rated
70 | Requirements not align with systems Project objectives are not achieved because requirements fail to align with other systems (e.g. duplicate functionality). | D |  |  | 0 | Not rated
71 | Requirements have compliance issues Project objectives are not achieved because requirements have compliance issues (i.e. law, audit, reporting) | L,R,D |  |  | 0 | Not rated
72 | Requirements are ambiguous Project objectives are not achieved because requirements are unclear and open to interpretation. | D |  |  | 0 | Not rated
73 | Requirements are low quality Project objectives are not achieved because requirements aren't fit for purpose. | $,T,D |  |  | 0 | Not rated
74 | Requirements are incomplete Project objectives are not achieved because requirements contain holes | $,T,D |  |  | 0 | Not rated
User Acceptance
75 | Users reject the prototype Project objectives are not achieved because users reject the prototype (require significant rework). | $,T |  |  | 0 | Not rated
76 | Inappropriate User Interface (UI) Project objectives are not achieved because the user interface doesn't allow users to complete end-to-end tasks. | $,T,D |  |  | 0 | Not rated
77 | User interface is low quality Project objectives are not achieved because the user interface is buggy, slow or difficult to use. | $,T,D |  |  | 0 | Not rated
78 | User interface isn't accessible Project objectives are not achieved because the user interface does not meet Easy-of-Access requirements (e.g. employment or consumer law). | $,T,D |  |  | 0 | Not rated
79 | Project reduces business productivity Project objectives are not achieved because users see the product(s) as reducing their productivity. | $,T,D |  |  | 0 | Not rated
80 | Project reduces innovation Project objectives are not achieved because users see the product(s) as a roadblock to innovation. | $,T,D |  |  | 0 | Not rated
81 | Product disrupts business metrics (KPIs) Project objectives are not achieved because the product disrupts measurements of objectives (causes business KPIs to worsen). | $,T,D,I |  |  | 0 | Not rated
82 | Users reject the product Project objectives are not achieved because users reject the product (yes, it could happen). |  |  |  | 0 | Not rated
Decisions & Issue Resolution & Approvals
83 | Decision delays Project objectives are not achieved because long decision turnaround time. | T |  |  | 0 | Not rated
84 | Decisions are ambiguous Project objectives are not achieved because stakeholders make decisions that are intentionally ambiguous (a responsibility avoidance technique). | T,D |  |  | 0 | Not rated
85 | Decisions are low quality Project objectives are not achieved because decisions aren't fit for purpose. | T,D |  |  | 0 | Not rated
86 | Decisions are incomplete Project objectives are not achieved because decisions don't address the issue or create more issues. | $,T,D |  |  | 0 | Not rated
87 | Delays to stakeholder approvals Project objectives are not achieved because of delays to stakeholder approvals. | T |  |  | 0 | Not rated
88 | Delays to financial approvals Project objectives are not achieved because of delays to financial approvals. | T |  |  | 0 | Not rated
89 | Delays to procurement processes Project objectives are not achieved because of delays due to procurement processes. | T |  |  | 0 | Not rated
90 | Delays to recruiting processes Project objectives are not achieved because of delays due to recruiting processes. | T |  |  | 0 | Not rated
91 | Delays to training Project objectives are not achieved because of delays due to team member training or training budget approval. | T |  |  | 0 | Not rated
92 | Project team lacks authority Project objectives are not achieved because project team lacks authority to complete work. | T |  |  | 0 | Not rated
93 | Authority is unclear Project objectives are not achieved because it's unclear who has the authority to accomplish a project objective. | T,D |  |  | 0 | Not rated
Organizational & External
94 | Fails to match the organization's culture Project objectives are not achieved because the project ails to match the organization's culture. For example, the organization's culture calls for employees to bring their own mobile devices to work (BYOD) and you build a user interface that only works on a specific device. | D |  |  | 0 | Not rated
95 | An organizational change disrupts the project Project objectives are not achieved because of organizational changes (i.e. merger or acquisition) | D |  |  | 0 | Not rated
96 | Conflict with vendor leads to project issues Project objectives are not achieved because the relationship with vendor turns to conflict and project issues mount. | $,T,D |  |  | 0 | Not rated
97 | Conflict between vendors leads to project issues Project objectives are not achieved because conflict between vendors leads to project issues | $,T,D |  |  | 0 | Not rated
98 | Vendors start late Project objectives are not achieved because vendors start later than expected. | T,D |  |  | 0 | Not rated
99 | Vendor components fail to meet requirements Project objectives are not achieved because a vendor misunderstands requirements or delivers components that are completely off the mark. | $,T,D |  |  | 0 | Not rated
100 | Vendor components are low quality Project objectives are not achieved because vendor components aren't fit for purpose. | $,T,D |  |  | 0 | Not rated
101 | Vendor components introduce third party liability Project objectives are not achieved because vendor components introduce liability (e.g. they violate patents or licenses). | $,D,R,L |  |  | 0 | Not rated
102 | Loss of intellectual property Project objectives are not achieved because vendors spy on you. | K,C |  |  | 0 | Not rated
103 | Third-party service quality is low Project objectives are not achieved because services procured for the project are not fit for purpose (i.e. consulting, IaaS, PaaS). | $,T,D |  |  | 0 | Not rated
104 | Legal & regulatory change impacts project Project objectives are not achieved because of legal & regulatory changes | $,T,D |  |  | 0 | Not rated
105 | Force Majeure (e.g. act of nature) impacts project Project objectives are not achieved because of major disruptions such as acts of nature. | $,T,D |  |  | 0 | Not rated
106 | Market forces impact project Project objectives are not achieved because of market changes (e.g. a market crash). | $,T,D |  |  | 0 | Not rated
107 | Industry change impacts project Project objectives are not achieved because of technology or business innovation changes your industry. | $,T,D |  |  | 0 | Not rated
Commercial
108 | Product doesn't sell Project objectives are not achieved because the product doesn't sell. | $,D,I |  |  | 0 | Not rated
109 | Product incurs legal liability Project objectives are not achieved because the product has quality issues that harm customers. | F,L,R,$,D,I |  |  | 0 | Not rated
110 | Product negatively affects brand Project objectives are not achieved because the product has quality issues that damage organization's brand. | R,I,D |  |  | 0 | Not rated
111 | Product negatively affects reputation Project objectives are not achieved because the product generates negative publicity and/or damages customer relationships. | R,I,D |  |  | 0 | Not rated
[5 empty] | 0 | Not rated
[5 empty] | 0 | Not rated
[5 empty] | 0 | Not rated
[5 empty] | 0 | Not rated
Note on A1: Risk ID: a simple number for reference
Note on C1: Consequence - outcome of an event affecting MCAP’s objectives
Note on D1: Impact - The assessed potential impact resulting from a compromise of the confidentiality, integrity, or availability of an information type, expressed as a value of low, moderate, or high.
Note on E1: Probability - a weighted factor based on a subjective analysis of the likelihood of occurrence that a given threat is capable of exploiting a given vulnerability or a set of vulnerabilities. For Probability consider the following frequency guideline: * Exceptional - few times per century * Very Unlikely - once a decade * Unlikely - once a year * Possible - once a month * Likely - every few days * Frequent - several times a day
Note on F1: Residual Risk Rate
Note on B16: Eugene Taylashev: Agile methodology welcomes changes to the initial scope

## Terms & Definitions
Term | MCAP Definition | Ref
Access control | Mechanisms that limit availability of information or information-processing resources only to authorized persons or applications | PCI-DSS
Adversary | Individual, group, organization, or government that conducts or has the intent to conduct detrimental activities. | DHS Risk Lexicon
Asset | Anything that has value to the organization and which therefore requires protection. See also 'information asset' | ISO/IEC 27005:2011
Attack | Any kind of malicious activity that attempts to collect, disrupt, deny, degrade, or destroy information system resources or the information itself. | CNSSI No. 4009
Authentication | Verifying the identity of a user, process, or device, often as a prerequisite to allowing access to resources in an information system. | FIPS 200
Availability | Ensuring timely and reliable access to and use of information. | 44 U.S.C., Sec. 3542
Compensating Security Control | A management, operational, and/or technical control (i.e., safeguard or countermeasure) employed by an organization in lieu of a recommended security control in the low, moderate, or high baselines that provides equivalent or comparable protection for an information system. | CNSSI No. 4009
Confidentiality | Preserving authorized restrictions on information access and disclosure, including means for protecting personal privacy and proprietary information. | 44 U.S.C., Sec. 3542
Consequence | outcome of an event affecting MCAP’s objectives. An event can lead to a range of consequences. A consequence can be certain or uncertain and in the context of information security is usually negative. | ISO/IEC 27005:2011
Control | measure that is modifying risk. Controls for information security include any process, policy, procedure, guideline, practice or organizational structure, which can be administrative, technical, management, or legal in nature which modify information security risk. | ISO/IEC 27005:2011
Criticality | A measure of the degree to which an organization depends on the information or information system for the success of a mission or of a business function. | NIST SP 800-60
Cyber Attack | An attack, via cyberspace, targeting an enterprise’s use of cyberspace for the purpose of disrupting, disabling, destroying, or maliciously controlling a computing environment/infrastructure; or destroying the integrity of the data or stealing controlled information. | CNSSI No. 4009
Cyber Security | The ability to protect or defend the use of cyberspace from cyber attacks. | CNSSI No. 4009
Cyberspace | A global domain within the information environment consisting of the interdependent network of information systems infrastructures including the Internet, telecommunications networks, computer systems, and embedded processors and controllers. | CNSSI No. 4009
Event | occurrence or change of a particular set of circumstances. An event can be one or more occurrences, and can have several causes. A negative event can sometimes be referred to as an “incident” or “accident”. | ISO/IEC 27005:2011
External context | external environment in which MCAP seeks to achieve its objectives. External context can include: the cultural, social, political, legal, regulatory, financial, technological, economic, natural and competitive environment, whether international, national, regional or local; key drivers and trends having impact on the objectives of the organization; and relationships with, and perceptions and values of, external stakeholders | ISO/IEC 27005:2011
Impact Level | The magnitude of harm that can be expected to result from the consequences of unauthorized disclosure of information, unauthorized modification of information, unauthorized destruction of information, or loss of information or information system availability. | CNSSI No. 4009
Impact Value | The assessed potential impact resulting from a compromise of the confidentiality, integrity, or availability of an information type, expressed as a value of low, moderate, or high. | CNSSI No. 1253
Information | Any communication or representation of knowledge such as facts, data, or opinions in any medium or form, including textual, numerical, graphic, cartographic, narrative, or audiovisual. | CNSSI No. 4009
Information Asset | A body of knowledge that is organized and managed as a single entity. Like any other corporate asset, an organization's information assets have financial value. That value of the asset increases in direct relationship to the number of people who are able to make use of the information.
Information Owner | Official with statutory or operational authority for specified information and responsibility for establishing the controls for its generation, classification, collection, processing, dissemination, and disposal. | CNSSI No. 4009
Information Resources | Information and related resources, such as personnel, equipment, funds, and information technology. | 44 U.S.C., Sec. 3502
Information Security | The protection of information and information systems from unauthorized access, use, disclosure, disruption, modification, or destruction in order to provide confidentiality, integrity, and availability. | 44 U.S.C., Sec. 3542
Information System | A discrete set of information resources organized for the collection, processing, maintenance, use, sharing, dissemination, or disposition of information. | 44 U.S.C., Sec. 3502
Information System Owner | Official responsible for the overall procurement, development, integration, modification, or operation and maintenance of an information system. | NIST SP 800-30
Integrity | Guarding against improper information modification or destruction, and includes ensuring information nonrepudiation and authenticity. | 44 U.S.C., Sec. 3542
internal context | internal environment in which MCAP seeks to achieve its objectives. Internal context can include: governance, organizational structure, roles and accountabilities; policies, objectives, and the strategies that are in place to achieve them; the capabilities, understood in terms of resources and knowledge (e.g. capital, time, people, processes, systems and technologies); information systems, information flows and decision-making processes (both formal and informal); relationships with, and perceptions and values of, internal stakeholders; the organization's culture; standards, guidelines and models adopted by the organization; and form and extent of contractual relationships. | ISO/IEC 27005:2011
Level of risk | magnitude of a risk, expressed in terms of the combination of consequences and their likelihood. | ISO/IEC 27005:2011
Likelihood | chance of something happening | ISO/IEC 27005:2011
Likelihood of Occurrence | A weighted factor based on a subjective analysis of the probability that a given threat is capable of exploiting a given vulnerability or a set of vulnerabilities. | CNSSI No. 4009
Management Controls | The security controls (i.e., safeguards or countermeasures) for an information system that focus on the management of risk and the management of information system security. | FIPS 200
Operational Controls | The security controls (i.e., safeguards or countermeasures) for an information system that are primarily implemented and executed by people (as opposed to systems). | FIPS 200
Owner | See Information Owner and Information System Owner
Qualitative Assessment | Use of a set of methods, principles, or rules for assessing risk based on nonnumerical categories or levels. | DHS Risk Lexicon
Quantitative Assessment | Use of a set of methods, principles, or rules for assessing risks based on the use of numbers where the meanings and proportionality of values are maintained inside and outside the context of the assessment. | DHS Risk Lexicon
Residual risk | risk remaining after risk treatment. Residual risk can also be known as “retained risk” | ISO/IEC 27005:2011
Residual risk | Portion of risk remaining after security measures have been applied. | CNSSI No. 4009
Risk | Effect of uncertainty on objectives. Information security risk is often expressed in terms of a combination of the consequences of an information security event and the associated likelihood of occurrence. Information security risk is associated with the potential that threats will exploit vulnerabilities of an information asset or group of information assets and thereby cause harm to an organization. | ISO/IEC 27005:2011
Risk Analysis | process to comprehend the nature of risk and to determine the level of risk. Risk analysis provides the basis for risk evaluation and decisions about risk treatment. | ISO/IEC 27005:2011
Risk Assessment | overall process of risk identification, risk analysis and risk evaluation. | ISO/IEC 27005:2011
Risk Communication | continual and iterative processes that MCAP conducts to provide, share or obtain information, and to engage in dialogue with stakeholders regarding the management of risk. The information can relate to the existence, nature, form, likelihood, significance, evaluation, acceptability and treatment of risk. | ISO/IEC 27005:2011
Risk Criteria | terms of reference against which the significance of a risk is evaluated. Risk criteria are based on organizational objectives, and external and internal context. | ISO/IEC 27005:2011
Risk Evaluation | process of comparing the results of risk analysis with risk criteria to determine whether the risk and/or its magnitude is acceptable or tolerable. Risk evaluation assists in the decision about risk treatment. | ISO/IEC 27005:2011
Risk Identification | process of finding, recognizing and describing risks. Risk identification involves the identification of risk sources, events, their causes and their potential consequences. Risk identification can involve historical data, theoretical analysis, informed and expert opinions, and stakeholders’ needs. | ISO/IEC 27005:2011
Risk Management | coordinated activities to direct and control an organization with regard to risk. | ISO/IEC 27005:2011
Risk Treatment | process to modify risk. Risk treatment can involve: avoiding the risk by deciding not to start or continue with the activity that gives rise to the risk; taking or increasing risk in order to pursue an opportunity; removing the risk source; changing the likelihood; changing the consequences; sharing the risk with another party or parties (including contracts and risk financing); and retaining the risk by informed choice. | ISO/IEC 27005:2011
Security Policy | A set of criteria for the provision of security services. | CNSSI No. 4009
Stakeholder | person or organization that can affect, be affected by, or perceive themselves to be affected by a decision or activity | ISO/IEC 27005:2011
Threat | Condition or activity that has the potential to cause information or information processing resources to be intentionally or accidentally lost, modified, exposed, made inaccessible, or otherwise affected to the detriment of the organization. | PCI-DSS

## Reference Values
Consequences |  | VLOOKUP Values (do not edit)
F - Material Financial loss |  | Risk Rating
L - Legal actions | 0 | Not rated
R - Reputation damage | 1 | Low
U - Loss of users / customers | 2 | Low
C - Loss of competitive advantage | 3 | Low
K - Loss of knowledge / Intellectual Property | 4 | Low
I - Key stakeholders (e.g. Board, Shareholders) confidence loss | 5 | Medium
S - Loss of service / SLA | 6 | Medium
| 8 | Medium
Project specific consequences | 9 | High
$ - escalation of project costs (Cost) | 10 | High
T - activities will take longer than expected (Schedule) | 12 | High
D - the project will not deliver expected results (Performance) | 15 | High
| 16 | High
| 20 | Extreme
Business Impact (Pull-down values - edit only text) | 25 | Extreme
1-Insignificant
2-Minor
3-Moderate
4-Major
5-Catastrophic
Probability (Pull-down values -edit only text)
1-Rare
2-Unlikely
3-Possible
4-Likely
5-Almost certain